Terms of Reference

Education consultant specialised in children with sensory impairment (Hearing impairment, and associated speech impairments)

Description of activities implemented in DPRK

Handicap International (due to political reasons known in DPR Korea as European Union Programme Support Unit 7) has been operational in the DPRK since 2001 in coordination and collaboration of the Korean Federation for the Protection of the Disabled (KFPD). Currently HI is implementing projects in DPRK based on a 5 year operational strategy (2014-2018.), which has been jointly defined through a participatory process with the local partner. The overall objective of HI’s current operational strategy is to “strengthen the capacities of KFPD to promote equal opportunities, protection of rights and the participation of people with disabilities and the perception that they are contributing citizens of DPRK”. The HI program currently follows the three following pillars identified in the strategy, being implemented in Pyongyang and in 6 provinces:

(1) Support to disability focused actors in promoting rights and equal opportunity for people with disabilities with focus on special education, promotion of the Korean Disability Law (KDL) and the United Nations Convention on the Rights of Persons with Disabilities (UNCRPD) and implication of decentralised local actors;

(2) Improve the access and support to functional rehabilitation services for people with disabilities including children and women, putting emphasis on improving the acess to the functional rehabilitation services through decentralization of services, outreach mobile camps and a sustainable training system for rehabilitation professionals.

(3) Promote inclusive DRR practices, increase community resilience and reduce risk of disaster at school and community levels.

Education for children with disabilities

So far there is no real concept of inclusive or even an integrative education system in DPRK. There have been some attempts to place specialist centres next to mainstrem schools in Pyongyang but there is no reall integration between the two groups of children  The children with disabilities (mainly children with sensory disability) are mainly receiving  education in  special boarding schools. In total there are 11 special schools in DPRK, all are boarding schools and were established in the 1950's. All the schools were in very poor conditions and often lack basic and essential equipment  including teaching aids  for the education of children with disabilities, but this situation has now been improved thanks to the current project.  No schools or system of educational integration or inclusion has ever been developed for children with intellectual or multiple impairments, as has been the case in neighbouring Asian countries. The special school’s curriculum spans 10 school years whilst the mainstream curriculum spans 12 schools years. One main difference between the special and mainstream school curriculum is the emphasis on vocational training within the special schools (although the amendments applied to the Law in December 2013 pledge to revise this characteristic).

According to the Education Commission, all teachers deployed to the special schools have undergone general teacher training. There are no national or provincial special education training colleges. Instead the teachers allocated to the special schools receive up to six months in-house training from the senior teachers before starting their duty. Senior teachers are those who have been at the schools for the longest duration rather than those who are more qualified (certified). According to the school principals, it is compulsory for teachers and children to speak Sign language or to read Braille

Upon the request of KFPD, since December 2012 Handicap International/EUPS unit 7 has started working in the education sector in collaboration with the education commission and special education department. Since then HI has been implementing various projects   aimed at improving access to quality education for children with sensory impairments in 4 provinces of DPRK. So far projects has been implemented in 6 special schools; 4 schools for deaf and hard of hearing children and 2 schools for blind and visually impaired children and the following main activities have been carried out:

- Providing accurate information and promote the education and social inclusion of children with disabilities;

- Improving the school living environment, including the status of health and nutrition of the children with sensory impairments;

- Informing and giving useful input for the process of revision of the special schools’ curriculum;

- Supporting the diversification of teaching and learning methodologies through international expert. Use good practice and lessons learnt to inform national education policy and planning;

- Strengthening the capacity of KFPD to actively support the Education Commission to improve the education of children with disabilities.

Within  this frame work, in 2013 and 2014, 2 training sessions on child centered teaching methodologies for children with visual impairment were organized with the main task of delivering an introductory training on child centred methodologies to teachers employed in special schools. The training has been considered helpful by the teachers and by the Education Commission and requested to continue with this kind of training in future.

For this reason, in 2015 Handicap International planned a phase 2 of the project, funded by SIDA. This action includes 3 components:

- Improvement of teaching and learning methodologies for children with visual impairment and children with hearing impairments ( and associated speech impairments).

- Improvement of the coordination mechanism among stakeholders involved in special education

- Set up of an intranet among the school and the EC, so to facilitate communication and resources’ exchange.

With the on-going Sida funded project, two training sessions; one on child centred teaching methodologies for children with visual impirment and one on child centred teaching methodologies for children with hearing and speech impairment are planned. Training on child centred teaching methodologies for children with visual impairment has been conducted in 2016 and  training on child centred teaching methodologies for children with hearing and speech impairment is planned to be conducted in 2017.

Consultancy assignment:

This consultancy responds directly to the following project aim: “The education services for boys and girls with speech and  hearing impairments in the 4 target special schools for children with hearing impairment  are improved through improved teaching and learning methodologies”.

The consultant will contribute to the following project expected result: 80% of the trained teachers are able to use basic child-centred methodologies to better address the needs of girls and boys in special schools.

The consultant will be in charge of the activities set out below:

- Carrying out a baseline review of teachers’ needs

A baseline review, taking into consideration the report of the previous consultant and with the support of interviews with KFPD staff, principals and teachers when possible,the consultant  will identify teachers’ needs and capacities, and recommendations for further training will be implemented accordingly.

- Designing and delivering teacher training  curriculum focused on child centred methodologies and training of national facilitators

- Provide training report with detail of topic covered, methodology used for training, analysis of imporvment in skills and knoweldge of participants, challenges, oppertunities and furture recommendation.

A team of trainers will be trained on child-centred teaching and learning methodologies with a focus on teaching children with hearing impairments and associated speech impairments. Training materials will be prepared and be used in the sessions which will act as training manuals for the trainers and as a reference for the teachers. The manual will be tested during the teacher training and finalised before the end of the consultancy period.

The consultant will be under the responsibility of the HI DPRK Country Director (CD), who is also managing the education project. He/She will work in close collaboration with the CD and with KFPD counterpart. Various meetings with KFPD staff and Education Commission members will take place to give him/her a better understanding of education for children with disabilities in DPRK. School visits will be also organized according to local regulation (2 field trips per month of 1 day or more).

The consultancy is for a period of 45 days, including preparation of material and reporting. The arrival of the consultant  in the DPRK is foreseen in latest by 15th April 2017.

- Preparation(developing questionniare for baseline and conducting the base line): 7 days

- Designing and developing  teacher training curriculam based on finding of base line review (from disatnce) : 15 days

- Imparting training based on develop teacher training curriculam(in Pyongynag, DPRK): 16 days(including 10 days training)

- Training report: 7 days

Consultant Specification

The consultant will have to demonstrate an ability to understand the context, the political and logistical constraints prevalent in the country, and to be able to integrate these realities into his/her daily work.

The success of an expatriate in DPR Korea depends on both the personal and professional qualities that he/she brings to bare. An ability to demonstrate tolerance, patience, flexibility and self-reliance are important personality traits and are the key factors in determining the success of the applicant. The candidate should be psychologically strong enough to cope with the environment, be calm, and have well-tempered character showing maturity and diplomacy in decision-making. He/she must be a good communicator and know when and how to share information and to be able to organize his/her time with efficiency and flexibility according to possible restrictions imposed or administrative obligations.

Qualifications

- A Degree level and above in the field of special education in hearing and /or  speech impairment/ or equivalent ( e.g Speech and language therapy/ Audiology with extensive experience in school settings)

- Post graduate degree will be an advantage

Knowledge and experience required (Essential)

- Special Education and/  or Inclusive Education approaches ( 5 years +) Experience in special education of children with hearing impairment and associated speech impairments  (theory and practice);

- Teacher training manual design for teachers of children with disabilties ( including children with hearing impairment).

- Development of teaching and learning resource materials for children with disabilties ( including children with hearing and /or speech impairments) Knowledge of the UN Convention related to the Rights of Persons with Disabilities.

Knowledge and experience required (Desired)

- Experience of developing teacher training curriculums in special schools, particulalry for children with hearing impairments

- Experience in the context of DPRK

Language(s): 
        English is the working language; the candidate must be fluent in speaking and writing english .

Budget:

Expenses covered by Handicap International:

- Consultant fees: will be discussed according to consultant expectations;

- Field travel and accommodation in DPRK (Accommodation in Pyongyang in a shared flat, in hotel while in the field), logistic arrangement and authorisation will be insured by HI/EUPS Unit 7;

- International travel expenses: flight ticket, visa.

Expenses not covered by Handicap International:

- Food expenses or Perdiem;

- Health expenses and insurance(s).

HI/EUPS Unit7 will support the visa application and entry authorization for DPRK and will provide necessary document for Chinese visa if needed.

Administrative formalities

The application must be submitted Rajesh Chandra(DPRK.HI.director@handicap-int.org.cn) before the 31st January  2017 and should include:

- A curriculum vitae;

- A summary of how the applicant understands the assignment including constraints/opportunities;

- A good description of methodological approach;

- The consultancy fees expectations.

Please not that only short-listed candidate will be notified.

The development of DPRK’s nuclear program in 2005 led to an international crisis, and to the decision of the Korean government to expel, in 2006, all international NGOs. Only 6 of them, all European, were allowed to remain, but they cannot use their name and logo anymore. They are identified by a progressive number and they are called EUPS (European Unit Program Support). Handicap International is identified as EUPS Unit 7.

See Annex III for a summary document of this strategy.

“Improving inclusion and access to basic services for children, women and men with disabilities in DPRK”

Although the special schools are for children with hearing impairments, there are some children with associated speech impairments and others who have limited speech and have therefore been classified as being hearing impaired.

Experience on developing curriculum for teacher training on child centered methodologies for children with hearing impairment and associated speech impairment.